## Schedule
2020 | [20 empty] | 2021
| OCTOBER | [5 empty] | NOVEMBER | [6 empty] | DECEMBER | [6 empty] | jANUARY
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  |  | 1 | 2 | 3 | 4 | [6 empty] | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  | 1 | 2 | 3
5 | 6 | 7 | 8 | 9 | 10 | 11 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 4 | 5 | 6 | 7 | 8 | 9 | 10
12 | 13 | 14 | 15 | 16 | 17 | 18 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 11 | 12 | 13 | 14 | 15 | 16 | 17
19 | 20 | 21 | 22 | 23 | 24 | 25 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 18 | 19 | 20 | 21 | 22 | 23 | 24
26 | 27 | 28 | 29 | 30 | 31 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 28 | 29 | 30 | 31 |  |  |  | 25 | 26 | 27 | 28 | 29 | 30 | 31
30
25.10.2020 - 20.11.2020 - Thought about ideas of improving the Project 21.11.2020 - 22.11.2020 - Started learning about RPA frameworks of Python, about NumPy, Matplotlib and Pandas libraries | [27 empty] | Legend
Start of the Project
23.11.2020 - 03.12.2020 - Continued my learning of the libraries | [27 empty] | Work on the Project
05.12.2020 - 06.12.2020 - Started working on small parts of the project with the NMP libraries | [27 empty] | Overview of the project
07.12.2020 - 25.12.2020 - Started creating plots on test use cases | [27 empty] | Test of the product/Add new features
26.12.2020 - 27.12.2020 - Extracted the data and preprocessed it with BeautifulSoup4 library | [27 empty] | Final Test of the product
28.12.2020 - 08.01.2021 - Worked on preprocessing, creating the project plots | [27 empty] | Demo Day
09.01.10.2021 - 10.01.2021 - Tested the project, updated the technical documents | [27 empty] | Days passed
Project Schedule | [27 empty] | Important Updates on Project
Made by Vodă Darian-Florian